## Slide 1
MERIDIAN MANUFACTURING · 401(K) PLAN
Executive Handoff
Summary
Overview of the corporate retirement plan process — transition from implementation to ongoing service
Prepared by the Transition Team · July 2026 · Confidential

## Slide 2
AGENDA
What this briefing covers
1
Plan at a glance
Assets, participants, and headline metrics
2
Project status
Where the transition stands today
3
Milestones
What is complete and what remains
4
Work stream detail
Status across all five work streams
5
Risks & decisions
Open items requiring executive attention
6
Priorities & lessons
The 90-day runway and what we learned
Executive Handoff Summary · Meridian Manufacturing 401(k)
02

## Slide 3
PLAN AT A GLANCE
A healthy plan, ready for day-to-day service
$84.2M
PLAN ASSETS
Up from $78.6M at conversion
1,247
PARTICIPANTS
Across 4 manufacturing sites
93%
ENROLLMENT
Auto-enroll at 6% default
7.4%
AVG. DEFERRAL
Target: 8.0% by year-end
Why it matters: Meridian converted from a bundled recordkeeper in March with zero missed payrolls. Participation and deferrals are already ahead of plan-design assumptions, which puts the plan on track for its first favorable committee review in Q4.
Executive Handoff Summary · Meridian Manufacturing 401(k)
03

## Slide 4
EXECUTIVE OVERVIEW
Why this handoff, and why now
The 14-month implementation of the Meridian Manufacturing 401(k) plan is complete. Conversion, payroll integration, and the first full quarter of live operation have all closed without material issues.
This briefing transfers ownership from the implementation team to the ongoing service team. It captures the state of the plan, the open items that need watching, and the commitments made to the client along the way.
Clean conversion
3,900 records migrated; reconciliation variance of $0.00 at close.
Client relationship
Committee meets quarterly; CFO is the decision maker of record.
First-year calendar
Compliance testing, audit support, and 5500 filing all scheduled.
Executive Handoff Summary · Meridian Manufacturing 401(k)
04

## Slide 5
PROJECT STATUS
88% complete, on track
ON TRACK
Chart: 
| Recordkeeping | Payroll & data | Compliance | Communications | Advisory
Complete | 100 | 95 | 90 | 80 | 72
THIS PERIOD
Closed final payroll-file exceptions with ADP
Delivered enrollment kits to the two Ohio plants
Scheduled Q3 investment committee review
NEXT PERIOD
Launch managed-account advisory pilot
Complete Spanish-language education sessions
Executive Handoff Summary · Meridian Manufacturing 401(k)
05

## Slide 6
MILESTONES
Five gates from signature to steady state
Contract signed
May 2025
Data conversion
Feb 2026
Go-live
Mar 2026
First quarter close
Jun 2026
Steady-state handoff
Sep 2026
4 of 5 gates complete — the September handoff closes the implementation and moves Meridian to the ongoing service calendar.
Executive Handoff Summary · Meridian Manufacturing 401(k)
06

## Slide 7
WORK STREAM STATUS
Five streams, one watch item
WORK STREAM
OWNER
STATUS
NOTE
Recordkeeping & conversion
D. Alvarez
COMPLETE
Zero reconciliation variance at close
Payroll & data integration
S. Kim
COMPLETE
360° feed live with ADP since April
Compliance & testing
R. Osei
ON TRACK
ADP/ACP testing passes on preliminary data
Participant communications
J. Whitfield
ON TRACK
Two of three education waves delivered
Advisory & managed accounts
M. Torres
AT RISK
Pilot start slipped 3 weeks — vendor contract
Executive Handoff Summary · Meridian Manufacturing 401(k)
07

## Slide 8
RISK OVERVIEW
Three risks worth executive attention
HIGH
Advisory pilot delay
Vendor contract for managed accounts is 3 weeks behind. If unsigned by Aug 15, the pilot moves to Q4 and a client commitment is missed.
Mitigation: escalated to vendor VP; fallback SOW drafted.
MEDIUM
HR contact turnover
Meridian's benefits manager — our primary contact — departs in August. Institutional knowledge of payroll quirks leaves with her.
Mitigation: transition binder delivered; successor shadowing calls.
LOW
Audit readiness
First plan audit lands in Q1 2027. Auditor selection is late on the client side, compressing the PBC document window.
Mitigation: pre-built audit package; reminder cadence with CFO.
Executive Handoff Summary · Meridian Manufacturing 401(k)
08

## Slide 9
STAKEHOLDERS & DECISIONS
Who to know, what was decided
KEY STAKEHOLDERS
LC
Laura Chen
CFO — plan sponsor decision maker
RB
Rob Bauer
Plan committee chair, quarterly reviews
AN
Anita Novak
Incoming benefits manager (from Aug)
GP
Gary Price
Advisor of record, Price Retirement Group
DECISIONS ALREADY MADE
Auto-enrollment at 6% with 1% annual escalation to 10% — approved Nov 2025
QDIA mapped to target-date suite, R6 shares — approved Jan 2026
Per-head fee structure locked for 3 years — signed May 2025
Managed-account pilot for 55+ cohort — approved Jun 2026, pending vendor
Executive Handoff Summary · Meridian Manufacturing 401(k)
09

## Slide 10
THE 90-DAY RUNWAY
Immediate priorities
30 DAYS
Sign managed-account vendor SOW and confirm pilot cohort of 120 participants.
60 DAYS
Complete benefits-manager transition; run payroll fire-drill with the new contact.
90 DAYS
Deliver steady-state handoff gate and first ongoing-service committee review.
Lessons learned: start payroll-file testing six weeks earlier than the plan calls for; assign a named backup for every client contact; and put vendor contracts on the critical path from day one.
Questions → transition-team@example.com