## Slide 1
CLIENT ONBOARDING PLAYBOOK
Evergreen Health
403(b) Plan
Ninety days from signature to steady state — the phase-by-phase playbook for the onboarding team
Onboarding Practice · July 2026 · v2.1

## Slide 2
AT A GLANCE
The client, the clock, the commitment
6,800
ELIGIBLE EMPLOYEES
Across 11 hospital and clinic sites
$212M
PLAN ASSETS
Converting from two legacy vendors
90 days
TO STEADY STATE
Signature July 1 → go-live Sept 29
4 phases
ONE PLAYBOOK
Discover, build, convert, embed
The stakes: Evergreen left its last provider over a botched conversion. Every promise in this playbook was made in the finals presentation — the first 90 days are where we prove they chose right.
EVERGREEN HEALTH 403(B) · ONBOARDING PLAYBOOK
2

## Slide 3
THE ARC
Four phases in ninety days
1
DISCOVER
Days 1–15
Payroll census, plan document review, vendor data audit, stakeholder map.
2
BUILD
Days 16–45
Recordkeeping setup, payroll bridges, investment lineup, comms plan.
3
CONVERT
Days 46–75
Blackout window, asset transfer, reconciliation, go-live checks.
4
EMBED
Days 76–90
Enrollment push, manager training, first payroll cycles, handoff.
EVERGREEN HEALTH 403(B) · ONBOARDING PLAYBOOK
3

## Slide 4
KEY DATES
The dates the client is watching
Kickoff
Jul 8
Census locked
Jul 31
Blackout begins
Sep 2
Assets land
Sep 19
Go-live
Sep 29
Blackout is 27 days — shorter than the 45 the client suffered last time. That number is in the contract; protect it.
EVERGREEN HEALTH 403(B) · ONBOARDING PLAYBOOK
4

## Slide 5
THE TEAM
Who owns what
ROLE
OWNER
ACCOUNTABLE FOR
Onboarding lead
K. Ramirez
Single point of accountability; runs the weekly client call
Conversion analyst
T. Okafor
Census, data mapping, and the reconciliation ledger
Payroll integration
B. Lindqvist
Bridges for Workday + two legacy payroll feeds
Communications
A. Delgado
Blackout notices, enrollment campaign, site posters
Client sponsor
M. Vance (Evergreen)
Approvals, site access, and escalation on the client side
EVERGREEN HEALTH 403(B) · ONBOARDING PLAYBOOK
5

## Slide 6
THE HARD PART
Data and payroll, step by step
1
Census extract
Pull from Workday plus both legacy vendors; 6,800 records, 14 fields each.
2
Gap scrub
Match SSNs across systems; last conversion this size surfaced ~400 mismatches.
3
Bridge build
Automated 360° feed with Workday; manual bridge for the clinic payroll until Q1.
4
Parallel run
Two full payroll cycles run side-by-side before anyone cuts over.
5
Sign-off
Client payroll director signs the reconciliation ledger — no verbal approvals.
EVERGREEN HEALTH 403(B) · ONBOARDING PLAYBOOK
6

## Slide 7
COMMUNICATIONS
What employees hear, and when
JULY
“Change is coming”
Announcement letter, intranet banner, manager FAQ — signed by Evergreen's CHRO, not by us.
AUGUST
“What you need to do”
Blackout notice (legal), enrollment guide, three lunch-and-learns per site, Spanish and Tagalog versions.
SEPTEMBER
“You're live”
Go-live email, first-login campaign, on-site help desks the week of Sept 29, textline for floor staff.
EVERGREEN HEALTH 403(B) · ONBOARDING PLAYBOOK
7

## Slide 8
COMPLIANCE
Nothing optional on this page
404(a)(5) fee disclosure
Delivered with enrollment guide
Blackout notice (30-day rule)
Mails Aug 1 — legal approved
QDIA notice
With enrollment guide + annual repeat
ERISA fidelity bond check
Client bond covers new asset level
Plan document restatement
Counsel drafting; due before go-live
5500 filing responsibility
Transfers to us for plan year 2026
EVERGREEN HEALTH 403(B) · ONBOARDING PLAYBOOK
8

## Slide 9
SCORECARD
How Evergreen will grade us
Chart: 
| Enrollment rate | First-login rate | Deferral ≥ 5% | Beneficiary on file
Target | 85 | 70 | 60 | 75
Day-90 actual (tracking) | 88 | 64 | 58 | 71
THE ONE THAT MATTERS
Zero
missed or wrong payroll contributions in the first 90 days.
This is the number the CFO quoted back to us from the finals meeting.
EVERGREEN HEALTH 403(B) · ONBOARDING PLAYBOOK
9

## Slide 10
DAY 90 AND BEYOND
Plant it well,
then hand it over.
Steady-state review
Day-90 scorecard presented to the Evergreen committee with the full reconciliation ledger.
Named service team
Client meets their ongoing team in week 10 — no cold handoffs, two overlap calls minimum.
Year-one calendar
Compliance testing, audit package, and education waves booked before onboarding closes.
Onboarding Practice · playbook v2.1 · July 2026